## Slide 1: MSF Data warehouse
Iteration 38
19th Nov – 25th Nov
Showcase and status update

## Slide 2: AGENDA
Product Demo
Iteration 38 Results
Patch Release 1.2.2 Status
Iteration 39 Goals
RAIDs and Blockers

## Slide 3: Demo stories
    Dynamic visualizer – Ability to filter charts based on service type & ability for transversal users to view charts for OCP

## Slide 4: Iteration 38 results
Completed 3 stories totaling 4 points (Goal: 4 points)
    Features signed off in Med Dept. release
      Dynamic visualizer – Ability to filter charts based on service type
      Dynamic visualizer [Feedback] – Ability for transversal users to view charts for OCP
      Analyze files that failed bulk import in production, fix and import fixed files
Key Activities
    Corrected files that failed bulk import in production and did a successful re-import
    Started discussions on field app usability testing

## Slide 5: Patch release 1.2.2 status
‘RAIDs & Blockers’ slide has details of story on hold.
Chart: 
| #19 Dynamic Visualizer | #23 Migration | #34 Data setup
Hold | 1
QA Complete | 6 | 1

## Slide 6: Iteration 39 goals – 2 points
    Data management
      Ability to submit ER linelist data
    Data approval
      Create API for approving linelist data (event data) <to be estimated>
    Project management
      Have a fixed organization structure with 6 levels and module always at level 6

## Slide 7: Iteration 39 goals
Mingle Story No. | Release | Feature | Summary | Current Status | Est. Effort
362 | Field app | Data management | Submit ER linelist data | Dev in Progress | 2
 | Field app | Data approval | Create API for approving linelist data | Analysis in Progress | <to be estimated>
755 | Field app | Project management | Have a fixed organization structure | Dev. complete | 0

## Slide 8: RAIDS and blockers
Type | Description | Action by date | Action/Update | Owner
Blocker | Unable to implement the filter to show linelists belonging only to the new data model during module creation as programs don’t support addition of custom attributes. (Story #731 on hold) | - | [Update – 25th Nov] DHIS responded that this can be picked up in 2.18 release | 
Blocker | Adding/cleaning up of indicators is on hold waiting for input from Megan on the indicators that are required. (Story #686 on hold) | - | [Update – 25th Nov] TW (devs) shared information on indicators used in data visualizer favorite charts, dynamic visualizer and in DHIS dashboard. | -